## Sheet1
Environmentally Sustainable Community (ESC) Strategy | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Staff work with consultants | bar: Jan to May
Planning Commission/Park Board Review | bar: Feb; Jun; Oct; Feb
Council check-in points | bar: Apr; Dec
Staff prepares final draft of ESC Strategy | bar: Jul to Sep
Public meeting(s) | bar: Oct to Nov
Council adopts ESC Strategy
Staff prepares possible Plan and Code Amendments | bar: Dec to Jan
Plan and Code Amendments heard by Planning Commission | bar: Feb to Mar
Council adoption of Plan and Code Amendments
Council considers implementation as part of Budget
Legend
Planning Commission meeting
Other Action
Council adoption